# Go-To-Market Plan — Commercializing the Locksmith Voice Agent

Plain-language plan to take the working product (multi-tenant call → SMS dispatch, shared Vapi assistant, outreach engine) and turn it into a business we can sell — starting with cold calls. Each item has a “What we’re doing” (so anyone can pick it up and brief their own helper) and a “Why”. Work is split across Abdul, Miguel, and Jordan.

Status: ☐ not started · ◐ in progress · ☑ done.

## Friday gate (2026-06-26) — minimum to START cold calling

Goal: by end of Friday’s meeting, be able to start cold calling. “Ready to cold call” is a LOWER bar than “ready to charge a customer” — there’s a lag of days/weeks between the first call and the first signed customer, so the heavy items (legal, A2P/10DLC, billing, onboarding automation) finish during the sales pipeline, not before the first dial.

Minimum to dial: - ☐ A price to quote — Abdul + Miguel, decided at the meeting (the one hard blocker). - ☐ A v1 cold-call pitch + basic objection answers — Abdul. - ☑ A working demo — the live M&J line already proves the product (dedicated demo number is a nice-to-have, not a blocker). - ☑ A booking link to send prospects — Calendly ready (https://calendly.com/miguel-dispango/30min); Jordan embeds it in the landing page. - ☑ A target call list — already in outreach/contacted.csv (Calgary shops). - ◐ Basic credibility — one-page site (Jordan) ideal; not strictly blocking first calls.

NOT required to start calling (must land before the first close/switch-on, not before the first dial): incorporation, legal docs, A2P/10DLC, billing, onboarding automation, monitoring.

Discipline: don’t cold-call faster than we can onboard. Start with a small pilot batch so the first “yes” isn’t left unserved while we finish contracts + SMS registration.

## Near-term: test the setup at the next meeting

- Dry-run the full onboarding with Jordan playing a customer. Walk Jordan through the entire setup as if he just signed up, start to finish.

  - What we’re doing: rehearsing the real customer experience to find every confusing or broken step before a paying customer hits it.

  - Why: the fastest way to discover gaps in the setup process is to actually run it on a “fake customer.” Output = a punch-list of what to fix/automate.

## Abdul

- Incorporate the company.

  - What we’re doing: registering a corporation (federal, ~$200, protects the name Canada-wide) so the company holds the contracts, money, and risk — not us personally.

  - Why: once we take payments and handle people’s call data, an unincorporated setup leaves our personal assets exposed if anything goes wrong.

- GST/HST registration + business bank account.

  - What we’re doing: registering for HST (required over $30k/yr, fine to do early) and opening a dedicated business bank account.

  - Why: needed to invoice correctly and to keep the “company vs personal” wall real.

- Uptime monitoring + alerting (incl. Vapi balance safety).

  - What we’re doing: a watcher that pings the live webhook and alerts us fast if it breaks, plus a Vapi low-balance alert + auto-reload.

  - Why: all customers run off the system; if the webhook dies or the prepaid balance hits $0, lines go silent and we must know before a customer does.

- Cold-call pitch / script.

  - What we’re doing: write the actual pitch used on calls — opener, the value in one line, answers to the common objections, and the ask (book a demo).

  - Why: this is what turns a cold dial into a booked demo; Abdul is doing the calling, so Abdul owns the script. Needed for the Friday gate.

- Pricing (with Miguel — see Decisions).

## Miguel

- ◐ Privacy Policy.

  - What we’re doing: a public document stating how we collect/store/delete caller data (names, numbers, addresses, transcripts).

  - Why: legally required under Canadian privacy law (PIPEDA) because we handle real people’s personal information.

- ◐ Data Processing terms.

  - What we’re doing: the contract clause saying the locksmith owns their callers’ data and we only process it on their behalf.

  - Why: clarifies legal responsibility for the data and is expected by privacy law.

- ◐ Terms of Service.

- ◐ Customer contract (MSA) with a liability cap + SLA disclaimer.

  - What we’re doing: the agreement the customer signs, explicitly stating we do NOT guarantee zero missed calls and capping our liability.

  - Why: if our system hiccups and a locksmith misses a big emergency job, this is what protects us from being blamed for the lost revenue.

- ◐ Billing wired to service state.

  - What we’re doing: Stripe subscription + the “sign-contract-then-pay” flow, plus the rule for what happens on a failed payment (suspend vs keep serving).

  - Why: this is how we actually collect money and stop serving non-payers.

- ☐ SMS deliverability / A2P registration (provisional owner — confirm).

  - What we’re doing: checking with Twilio whether our Messaging Service + number need A2P/10DLC registration, and registering if so.

  - Why: carriers silently filter/block unregistered automated business texts. Our whole product is “we text you the lead” — if texts don’t deliver, the product is broken. Our number is a US number (+1 651), so US sending rules apply.

- ☐ Pricing (with Abdul — see Decisions).

## Jordan

- One-page website (Bengal/Dispango domain).

  - What we’re doing: a single page — what it does, a demo number to call, “book a demo” button.

  - Why: a cold-called locksmith Googles us; no site = no trust = no deal.

- Demo asset — a dedicated demo number/persona, separate from M&J’s real line.

  - What we’re doing: a “show-off” number a prospect can call to hear the AI, that doesn’t pollute a real customer’s lead data.

  - Why: the live demo is the strongest part of the pitch; it needs its own sandbox.

- Defined sales motion.

  - What we’re doing: writing the exact step-by-step from cold call → demo → pitch + price → contract → payment → onboard.

  - Why: we have the front (outreach) and back (onboarding); the middle (how a call becomes a paying customer) is undefined.

- Calendar integration on the landing page.

  - What we’re doing: embed the Calendly booking widget into the landing page so a potential customer can schedule a meeting in one click.

  - Why: turns a website visitor into a booked demo with no back-and-forth.

  - Booking link to embed: https://calendly.com/miguel-dispango/30min

- Step-by-step setup document + new-customer runbook.

  - What we’re doing: one clear document with the EXACT setup steps (below), used both as our internal checklist and as the customer’s guide.

  - Why: setup must be repeatable by anyone, not just whoever built it. This is what we rehearse at the meeting.

  - Steps: (1) provision/assign a Vapi number → (2) create their clients row (business_name, agent_name, dispatch_phone, inbound_number, timezone) →

    - give them the call-forwarding setup guide (dial codes differ by phone type: cell vs landline vs VoIP) → (4) go-live verification (see below).

- Kanban board to present at Friday’s meeting.

  - What we’re doing: a visual board (columns like To-Do / In-Progress / Done) showing this whole plan and who owns what, ready to demo Friday.

  - Why: gives the team a shared, at-a-glance view of progress to run the meeting from.

- Merge + deploy the onboarding tool (with Miguel).

  - What we’re doing: reviewing the feat/admin-ui (admin page) and feat/billing-onboarding (billing) branches, merging them into main, and deploying them so they actually run.

  - Why: that onboarding software is built but only exists as draft code on GitHub — pushing to GitHub does NOT make it live. Merging + deploying turns it into a usable tool.

## Automate the setup (target: near-hands-off onboarding)

Goal: sign contract → pay → number auto-assigned → forwarding steps sent → test passes → live, with a human only watching. What’s needed:

- Admin onboarding tool live (merge + deploy, above) — a form that creates the customer’s row instead of hand-editing the database.

- Auto-provision the phone number via the Twilio/Vapi API (buy + assign a number from the form, no manual step).

- Auto-generate forwarding instructions for the customer’s specific carrier (we can’t change their phone, but we can hand them the exact dial codes automatically).

- Automated go-live test — a script that confirms the row is correct and the dispatch SMS fires, then flips the customer to “active.”

- Stripe + e-signature (Miguel’s billing branch) so contract → payment → provisioning chains automatically.

Build owners: items 1–2, 4 sit with Jordan + Miguel (onboarding tool); item 5 with Miguel.

## What “Go-Live Verification” means (the test before switch-on)

Before we tell a new locksmith “you’re live,” we run one test call that proves the whole chain works for THAT customer:

- Call their number ourselves, posing as a customer.

- Confirm the AI answers with their business name + agent name (not “M and J”, not a literal {{business_name}}).

- Confirm the dispatch SMS actually lands on the locksmith’s phone with the lead.

- Confirm the callback number in that text is correct.

Why: setup has several moving parts (number, the clients row, call forwarding on their phone, the prompt variables) and any one can be silently wrong. Skip the test and the customer’s first sign of failure is a real missed emergency lead. Plain version: don’t hand someone the keys without starting the car first. Lives inside Jordan’s runbook.

## Decisions needed (founders)

- Price / offer (Abdul + Miguel). The sales motion and the balance/cap plan both depend on it. If flat $199/mo, a high-volume customer could cost more than that in AI minutes → we need per-customer caps. If usage-based, we must meter usage anyway.

- Per-customer balance approach (Abdul + Miguel). One shared Vapi balance is a risk (empty it and every line dies). Two ways to fix:

  - Option A: a separate Vapi account per customer — true separate balances, but breaks the “one shared assistant” simplicity; heavy to operate.

  - Option B (recommended): one account + per-customer usage metering + spend caps + auto-reload — same protection (no customer drains the others, clear per-customer cost) without the overhead.

## Post-Friday priorities — close competitive gaps (vs voice.ai)

After Friday, work these to reach parity / differentiation against the competitor (voice.ai). Ordered by how often each shows up in a sales conversation:

- Customer dashboard / call-log (BUMPED from deferred). Competitor leads with a dashboard

  - “3× leads” stats; we show only an SMS. A simple per-customer call log turns “a script” into “a product.” Highest-priority gap.

- Appointment booking. Their AI books the job; ours captures + texts the lead. Add a booking/callback capability (or at least a strong “instant warm lead” story).

- Live human transfer / escalation. Competitor escalates urgent calls to dispatch/tech live; we modeled answer_mode: human_first but haven’t built the warm transfer.

- Per-shop FAQ config. Let the agent answer service-area / hours / pricing-basics per shop (a per-client FAQ field).

- CRM / dispatch-software integration. Lower priority — most solo shops don’t run one.

- Social proof. An M&J case study (“caught X after-hours leads in month one”) to counter their “350+ shops.”

Compete on a different axis too: Canadian/CASL-native, local owner-run service, and price.

## Deferred (nothing right now)

- The customer dashboard moved up to Post-Friday priorities above.

## Are we ready to commercialize once this is done?

Yes — ready to start, via cold calls, with two conditions: - Start with a small pilot (1–3 customers), not a blast — use the first few to shake out onboarding bugs and prove reliability before scaling outreach. - Monitoring + the Vapi balance safety net must be solid first — we’re handling other people’s emergency calls; downtime = lost leads + trust/liability hit.

The tech (the hard part) is essentially done. The gap to revenue is the legal wrapper + SMS deliverability + a repeatable/automated onboarding + billing. Land the assigned items and we can confidently take our first paying locksmith. “Ready” = ready to begin and onboard a controlled first batch — not “everything finished.”

### Still worth a thought (not blockers)

- Customer support / who responds when a customer says “my calls stopped” (even an informal channel + response-time expectation).

- Data deletion mechanism — the privacy policy will promise we can delete a customer’s data; the button/script to actually do it should exist.

- Cancellation / refund handling (part of billing).